## Field map
CRM migration field map and plan
Jinnflow · jinnflow.com/guides/crm-migration-plan/ · Every field you're moving, with value mapping.
Object | Old field | New field | Type | Value mapping / transformation | Moving?
Contact | Mobile | Phone | Phone | Reformat to +971… | Yes
Deal | Stage | Deal stage | Pipeline | 'Proposal' → 'Quote sent' | Yes
Contact | Lead Source | Lead source | Dropdown | 'FB', 'Facebook Ads' → 'Meta ads' | Yes

## Plan
CRM migration field map and plan
Jinnflow · jinnflow.com/guides/crm-migration-plan/ · In order.
# | Item | How to do it / what good looks like | Status | Owner | Notes
Prepare
1 | Decided what moves (and what's archived) |  | To do
2 | Data cleaned in export |  | To do
3 | New pipeline, fields, owners designed |  | To do
Import order
4 | 1. Users |  | To do
5 | 2. Companies |  | To do
6 | 3. Contacts linked to companies |  | To do
7 | 4. Deals linked |  | To do
8 | 5. Activities and notes |  | To do
9 | Test import of ~100 records checked, then deleted |  | To do
Rebuild
10 | Website forms |  | To do
11 | WhatsApp / inbox |  | To do
12 | Store, accounting, ad platform syncs |  | To do
13 | Automations, sequences, reminders |  | To do
14 | Reports and dashboards |  | To do
Cut-over
15 | Old CRM read-only |  | To do
16 | Delta import done |  | To do
17 | Forms and integrations switched |  | To do
18 | Live test enquiry end to end |  | To do
19 | Sales meeting run from new pipeline |  | To do
Done