## Reset plan
30-day CRM reset plan
Jinnflow · jinnflow.com/guides/why-nobody-uses-your-crm/ · Diagnose first, then work week by week.
# | Item | How to do it / what good looks like | Status | Owner | Notes
Diagnosis
1 | Leads arrive automatically? | Compare last month's enquiries (forms, WhatsApp, calls) with new CRM records. | To do
2 | WhatsApp connected? | Where were the last ten deals actually negotiated? | To do
3 | Required fields ≤ 5? | Count required fields on a new deal. | To do
4 | Stage exit rules agreed? | Ask three people what moves a deal into each stage. | To do
5 | Sales meeting runs from the CRM? | What's on screen in the weekly meeting? | To do
6 | No side spreadsheets? | Search Drive for 'leads', 'pipeline', 'clients'. | To do
7 | Mobile app usable? | Time logging a call + follow-up on a phone. | To do
Week 1: inputs
8 | Connect website forms | Form → CRM with source field. | To do
9 | Connect booking and ad lead forms |  | To do
10 | Decide WhatsApp logging | Native integration, shared inbox, or a rule for manual logging. | To do
11 | Import open deals from spreadsheets | Then make the sheet read-only. | To do
Week 2: simplify
12 | Cut required fields | Use the field audit sheet. | To do
13 | Write one exit rule per stage |  | To do
14 | Hide unused fields |  | To do
15 | Merge duplicates |  | To do
Week 3: habits
16 | Pipeline meeting runs from CRM views |  | To do
17 | Every open deal has a next step + date |  | To do
18 | Overdue follow-up reminders on |  | To do
Week 4: payoff
19 | 'My deals today' view for each salesperson |  | To do
20 | One manager report people actually use |  | To do
21 | Ask the team for the top 2 annoyances and fix them |  | To do
Done

## Field audit
30-day CRM reset plan
Jinnflow · jinnflow.com/guides/why-nobody-uses-your-crm/ · One row per field on deals/contacts. Keep only what you follow up or report on.
Field | Object (deal/contact) | Currently required? | Used in follow-up? | Used in a report? | Decision | Notes