## Redirect map
Migration redirect map and checklist
Jinnflow · jinnflow.com/guides/seo-safe-website-migration/ · Every URL with traffic or links. Sort by clicks + sessions; test every row on launch day.
Old URL | Search clicks (12 mo) | Sessions (12 mo) | External links | New URL (or 410) | Status after test | Result

## Checklist
Migration redirect map and checklist
Jinnflow · jinnflow.com/guides/seo-safe-website-migration/ · Based on Google's site move documentation.
# | Item | How to do it / what good looks like | Status | Owner | Notes
Plan
1 | One big change at a time (domain, platform, design) |  | To do
2 | Launch in a quieter period |  | To do
3 | Old and new sites verified in Search Console | Domain change | To do
Build
4 | Self-referencing canonicals on new site |  | To do
5 | Internal links updated to new URLs |  | To do
6 | New sitemap ready |  | To do
7 | Tracking moved |  | To do
8 | Content that ranks kept |  | To do
Launch
9 | Redirects on; every mapped URL tested |  | To do
10 | noindex / robots.txt blocks removed |  | To do
11 | New sitemap submitted |  | To do
12 | Change of Address submitted (domain change only) |  | To do
13 | Business Profile, social, ads, signatures updated |  | To do
14 | Top linking sites asked to update |  | To do
Monitor (3 months)
15 | New URLs indexing; old dropping |  | To do
16 | 404s fixed weekly |  | To do
17 | Clicks by page vs before |  | To do
18 | Enquiries / sales vs before |  | To do
19 | Redirects kept 1 year+; old domain renewed |  | To do
Done