## Checklist
Replatforming checklist and data map
Jinnflow · jinnflow.com/guides/ecommerce-replatforming-checklist/ · Inventory → migrate → rebuild → test → launch → monitor.
# | Item | How to do it / what good looks like | Status | Owner | Notes
Data
1 | Products: variants, SKUs, images, SEO fields |  | To do
2 | Customers + marketing consent |  | To do
3 | Account invitation / reset plan | Passwords usually can't move | To do
4 | Order history decided |  | To do
5 | Pages, blog, policies, navigation |  | To do
6 | Gift cards / store credit balances |  | To do
SEO
7 | URL inventory + redirect map |  | To do
8 | 301s tested |  | To do
9 | Sitemap submitted |  | To do
10 | Search Console monitored |  | To do
Operation
11 | Payments: cards, Apple Pay, COD, instalments |  | To do
12 | Shipping zones, rates, courier |  | To do
13 | VAT settings |  | To do
14 | Email flows reconnected |  | To do
15 | Accounting / CRM syncs |  | To do
16 | Marketplaces + inventory sync |  | To do
17 | GA4, Ads, Meta, TikTok tracking |  | To do
Testing
18 | Real orders with each payment method (refunded) |  | To do
19 | Discounts, gift cards, COD, delivery by emirate |  | To do
20 | Order emails + WhatsApp updates |  | To do
21 | Orders in accounting, CRM, courier |  | To do
22 | Mobile |  | To do
Launch week
23 | Quiet day; no sale running |  | To do
24 | Old store frozen during final sync |  | To do
25 | Domain switched, redirects on |  | To do
26 | Daily monitoring log |  | To do
Done

## Launch monitoring
Replatforming checklist and data map
Jinnflow · jinnflow.com/guides/ecommerce-replatforming-checklist/ · Compare with a normal week.
Date | Orders | Normal daily orders | vs normal | Payment failures | 404s found | Search clicks | Customer issues