## Checklist
Website launch SEO checklist
Jinnflow · jinnflow.com/guides/website-launch-seo-checklist/ · Work top to bottom. Most launch drops come from noindex, redirects or canonicals.
# | Item | How to do it / what good looks like | Status | Owner | Notes
Before: indexing
1 | No noindex on pages meant for search |  | To do
2 | robots.txt doesn't block the live site |  | To do
3 | Staging protected / noindexed |  | To do
4 | One version: https + www or non-www | Others redirect | To do
5 | Canonicals self-referencing, not to staging |  | To do
Before: page basics
6 | Unique title per page | See Pages sheet | To do
7 | Unique meta description |  | To do
8 | One H1 per page |  | To do
9 | Descriptive URLs |  | To do
10 | Images compressed + alt text |  | To do
11 | No orphan pages |  | To do
Before: redirects
12 | Old URL list from sitemap, analytics, Search Console |  | To do
13 | Each old URL mapped |  | To do
14 | 301s, one hop, no chains |  | To do
15 | Removed content returns 404/410 |  | To do
Before: experience and tracking
16 | Mobile check |  | To do
17 | Core Web Vitals: LCP ≤2.5s, INP ≤200ms, CLS ≤0.1 |  | To do
18 | Forms, phone, WhatsApp work |  | To do
19 | Organization / LocalBusiness structured data |  | To do
20 | Analytics key events firing |  | To do
21 | Ad conversion tracking moved |  | To do
Launch day
22 | Staging blocks removed |  | To do
23 | Top 20 old URLs redirect correctly |  | To do
24 | Sitemap submitted |  | To do
25 | URL Inspection on key pages |  | To do
26 | Test enquiry reaches CRM + analytics |  | To do
27 | Business Profile, social, ads updated |  | To do
After
28 | Days 1-3: indexing errors, 404s | Search Console | To do
29 | Week 1: traffic + key events vs before |  | To do
30 | Weeks 2-4: clicks by page |  | To do
31 | Month 2: rankings + enquiries for main services |  | To do
Done

## Pages
Website launch SEO checklist
Jinnflow · jinnflow.com/guides/website-launch-seo-checklist/ · One row per important page. Lengths are calculated.
URL | Title | Title length | Meta description | Desc length | H1 | Indexable? | Checked